## general_report
Key | Summary | Reporter | severity | Status | Resolution | Created | Updated
VMI-3034 | iOS: Reduce music stream when there is an audio/video comment | Sai Chow | Major | Working As Designed | Won't Fix | 05/Oct/15 11:04 PM | 06/Oct/15 1:16 AM
VMI-3033 | iOS: Audio comments cause buffering | Sai Chow | Major | Fixed | Fixed | 05/Oct/15 10:50 PM | 30/Oct/15 4:40 AM
VMI-3032 | iOS: Music "clicks" when suspending or resuming the app | Sai Chow | Major | Working As Designed | Won't Fix | 05/Oct/15 10:48 PM | 06/Oct/15 12:49 AM
VMI-3031 | iOS: Verify that track changes during Go Live does provide an updated image to the service | Sai Chow | Major | Working As Designed | Won't Fix | 05/Oct/15 10:38 PM | 07/Oct/15 2:01 AM
VMI-3030 | iOS: App crashes when switching the camera facing front and back | Sai Chow | Critical | Fixed | Fixed | 05/Oct/15 10:31 PM | 30/Oct/15 4:18 AM
VMI-3021 | Mess with a navigation bar when adding an artist or an album to a playlist. | Peter Vibe | Major | Fixed | Fixed | 05/Oct/15 9:57 AM | 30/Oct/15 7:34 AM
VMI-3020 | Android: When playback of broadcast starts information about track displays as unknown in mini-player | Aleksey Sofronov | Major | Fixed | Fixed | 05/Oct/15 8:34 AM | 06/Oct/15 4:54 AM
VMI-3019 | Android: Play/pause button has incorrect position in FSP when listen to broadcast | Aleksey Sofronov | Minor | Fixed | Fixed | 05/Oct/15 8:23 AM | 06/Oct/15 4:54 AM
VMI-3018 | Android: "Add to Favorites" button doesn't work in FSP during listen to broadcast | Aleksey Sofronov | Major | In Progress | Unresolved | 05/Oct/15 8:19 AM | 17/Nov/15 10:29 AM
VMI-3017 | iOS: "Add to Favorites" button doesn't work in FSP during listening to broadcast | Aleksey Sofronov | Major | Working As Designed | Won't Fix | 05/Oct/15 8:16 AM | 06/Nov/15 9:30 AM
VMI-3016 | Android: There's no "Add to Favorites" button in Album Action Menu | Toma Panina | Major | Working As Designed | Won't Fix | 05/Oct/15 6:52 AM | 17/Nov/15 4:44 PM
VMI-3015 | Android: App crashes after attempt of adding to playlist | Toma Panina | Critical | Working As Designed | Won't Fix | 05/Oct/15 6:27 AM | 16/Oct/15 8:37 AM
VMI-3013 | Android: There's no "Go to Artist" button in Album Action Menu | Toma Panina | Major | Fixed | Fixed | 05/Oct/15 5:50 AM | 16/Oct/15 8:37 AM
VMI-3012 | Android: Like/ Unlike for the "Top Five" of the list does not works | Alexey Dudarev [QA] | Major | Blocked | Incomplete | 05/Oct/15 5:50 AM | 17/Nov/15 5:06 PM
VMI-3010 | iOS: Downloading of song doesn't work | Toma Panina | Critical | Working As Designed | Won't Fix | 05/Oct/15 4:31 AM | 17/Nov/15 4:44 PM
VMI-3008 | iOS: Duplicating in playlist after adding there a song | Toma Panina | Critical | Fixed | Fixed | 05/Oct/15 3:07 AM | 27/Oct/15 10:23 AM
VMI-3006 | Crucible is down | Maxim Drozdov | Critical | Working As Designed | Won't Fix | 05/Oct/15 2:36 AM | 05/Oct/15 2:38 AM
VMI-3005 | iOS: "Repeat" button works incorrect | Olga Tsygankova | Major | Working As Designed | Won't Fix | 05/Oct/15 2:24 AM | 27/Oct/15 5:23 AM
VMI-3003 | iOS: "Previous" button works incorrect | Olga Tsygankova | Major | Fixed | Fixed | 05/Oct/15 2:19 AM | 20/Oct/15 2:00 AM
VMI-3002 | iOS: Incorrect Song Details in FSP - (Share Live = N) - Pos. 1 - Implement Regular Player | Olga Tsygankova | Major | Fixed | Fixed | 05/Oct/15 2:14 AM | 28/Oct/15 12:00 AM
VMI-3001 | iOS: Incorrect Track Timestamp - Remaining in FSP (Pos 1) (Share Live = N) | Olga Tsygankova | Major | Fixed | Fixed | 05/Oct/15 2:04 AM | 20/Oct/15 2:00 AM
VMI-3000 | Desktop: Podcasts and iTunes U episodes are synced by the app | Aleksey Sofronov | Major | Working As Designed | Won't Fix | 05/Oct/15 1:51 AM | 06/Nov/15 1:10 AM
VMI-2999 | Android: View Song Info should be called View Track Info | Toma Panina | Minor | Working As Designed | Won't Fix | 05/Oct/15 1:40 AM | 17/Nov/15 4:44 PM
VMI-2998 | Desktop: PUT /sync/changes request isn't sent after track deletion | Aleksey Sofronov | Major | Fixed | Fixed | 05/Oct/15 1:29 AM | 28/Oct/15 4:00 AM
VMI-2997 | iOS: Go Live button (Vertigo logo) stay white when/after Go Live | Sai Chow | Major | Fixed | Fixed | 05/Oct/15 12:12 AM | 06/Oct/15 7:32 AM
VMI-2981 | Service: Connect - Feed posts showing future timestamps | Ryan Taylor | Major | Fixed | Fixed | 02/Oct/15 3:40 PM | 17/Nov/15 4:57 PM
VMI-2980 | API: Only GET or HEAD is supported | Ryan Taylor | Major | Fixed | Fixed | 02/Oct/15 1:46 PM | 05/Oct/15 5:28 AM
VMI-2967 | Desktop: Coverart that was added by iTunes isn't synced for tracks | Aleksey Sofronov | Major | Working As Designed | Won't Fix | 02/Oct/15 6:50 AM | 03/Nov/15 12:58 AM
VMI-2966 | Services: Сoverart of mediafiles can't be deleted | Aleksey Sofronov | Major | Fixed | Fixed | 02/Oct/15 5:38 AM | 16/Nov/15 4:11 AM
VMI-2965 | Services: Sync process isn't proctected from the errors of too long parameters | Aleksey Sofronov | Major | Fixed | Fixed | 02/Oct/15 2:44 AM | 13/Nov/15 2:34 AM
VMI-2964 | Services: JSON error appears from the service during receiving data by mobile client | Aleksey Sofronov | Major | Working As Designed | Won't Fix | 02/Oct/15 2:29 AM | 05/Oct/15 11:08 AM
VMI-2958 | Android: Logout screen crashes when you click the back button | James Shaffer | Critical | Fixed | Fixed | 01/Oct/15 12:34 PM | 10/Nov/15 1:44 AM
VMI-2947 | Android: Sign up date field navigation is not correct | James Shaffer | Minor | Fixed | Fixed | 01/Oct/15 10:53 AM | 06/Oct/15 7:35 AM
VMI-2946 | Android: Signup allows spaces in username | James Shaffer | Minor | Fixed | Fixed | 01/Oct/15 10:37 AM | 10/Nov/15 1:44 AM
VMI-2945 | iOS: Remove from My Collection for Artist, Album and Songs | Sai Chow | Major | Blocked | Unresolved | 01/Oct/15 1:46 AM | 17/Nov/15 9:51 AM
VMI-2929 | iOS: Missing frames from videos from kickflip sdk. | Sai Chow | Major | Working As Designed | Won't Fix | 30/Sep/15 9:34 PM | 17/Nov/15 10:17 PM
VMI-2928 | iOS: Missing end fragments when video comment ends | Sai Chow | Critical | Fixed | Fixed | 30/Sep/15 9:32 PM | 13/Nov/15 1:32 AM
VMI-2927 | iOS: Sharing Live crash when flipping the camera to front/back facing | Sai Chow | Major | Fixed | Fixed | 30/Sep/15 8:31 PM | 13/Nov/15 1:33 AM
VMI-2910 | iOS: Subsequent broadcast cause undesirable listenin experience | Sai Chow | Major | Fixed | Fixed | 30/Sep/15 3:22 AM | 16/Nov/15 12:37 AM
VMI-2907 | iOS: Blue tint is set on some action menu; icons show as blue | Sai Chow | Major | Fixed | Fixed | 30/Sep/15 1:03 AM | 06/Oct/15 7:54 AM
VMI-2875 | iOS: The End Ring looks flat on iOS 6+ | Sai Chow | Major | Working As Designed | Won't Fix | 29/Sep/15 3:49 AM | 16/Oct/15 2:05 AM
VMI-2874 | iOS: ListenIn Following | Sai Chow | Major | Fixed | Fixed | 29/Sep/15 3:25 AM | 16/Nov/15 6:12 AM
VMI-2873 | iOS: Profile Follow user | Sai Chow | Major | Fixed | Fixed | 29/Sep/15 3:22 AM | 16/Nov/15 4:28 AM
VMI-2857 | Verticast does not contain all the video fragments made by its caster | Sergey Bobrovsky | Major | Fixed | Fixed | 27/Sep/15 11:36 PM | 13/Nov/15 1:34 AM
VMI-2855 | iOS: Crashed when selecting my collection Favorite folder | Nathan Haley | Critical | Fixed | Fixed | 27/Sep/15 9:18 PM | 06/Oct/15 7:50 AM
VMI-2839 | Use user profile image url to broadcast event | Sai Chow | Major | Fixed | Fixed | 26/Sep/15 4:54 PM | 16/Nov/15 2:59 AM
VMI-2838 | iOS 9: Sign up page 1 and 2 need to update layout | Sai Chow | Major | Fixed | Fixed | 26/Sep/15 4:16 PM | 16/Nov/15 5:41 AM
VMI-2829 | iOS: Album filter does not work in My Collection | Sai Chow | Major | Ready For Testing | Unresolved | 26/Sep/15 2:17 AM | 17/Nov/15 10:08 AM
VMI-2828 | iOS: Artist filter does not work in My Collection | Sai Chow | Major | Ready For Testing | Unresolved | 26/Sep/15 2:16 AM | 17/Nov/15 10:07 AM
VMI-2813 | Services: /search/user/ API can't find anything | Aleksey Sofronov | Critical | Ready For Testing | Incomplete | 25/Sep/15 5:37 AM | 13/Nov/15 4:11 PM
VMI-2812 | Sync service returns not correct number of the playlist items on the request sync/playlist/{playlistID}/items | Peter Vibe | Major | Fixed | Fixed | 25/Sep/15 4:29 AM | 06/Oct/15 5:04 AM
VMI-2811 | iOS: Music interrupted when suspending or resuming the app | Sai Chow | Major | Working As Designed | Won't Fix | 25/Sep/15 2:38 AM | 06/Oct/15 12:48 AM
VMI-2810 | iOS: Artist landing page album list missing rows when scroll up and down | Sai Chow | Minor | Fixed | Fixed | 25/Sep/15 2:31 AM | 30/Oct/15 7:30 AM
VMI-2809 | iOS: Share Live count down sometimes start counting at 2 instead of 3 | Sai Chow | Minor | Fixed | Fixed | 25/Sep/15 2:29 AM | 13/Nov/15 1:35 AM
VMI-2808 | iOS: time property in broadcast event not = 0 | Sai Chow | Minor | Working As Designed | Won't Fix | 25/Sep/15 2:24 AM | 25/Sep/15 11:16 AM
VMI-2802 | iOS: Closing Playlist Action Menu inside Folder does not dismiss action menu | Thuy Copeland | Major | Working As Designed | Won't Fix | 24/Sep/15 5:38 PM | 29/Sep/15 2:57 AM
VMI-2796 | Android: Inconsistent list item layouts | Ryan Taylor | Major | Fixed | Fixed | 24/Sep/15 12:54 PM | 24/Sep/15 4:49 PM
VMI-2792 | Android: App crashes when attempting to share remote artist | Ryan Taylor | Critical | Ready For Testing | Unresolved | 24/Sep/15 12:20 PM | 06/Oct/15 11:40 AM
VMI-2790 | API: Browse's mock data image_urls need updated | Ryan Taylor | High | Fixed | Fixed | 24/Sep/15 10:28 AM | 01/Oct/15 5:37 AM
VMI-2783 | iOS: Fast double tap on action menu button open 2 instances of menu | Andrew Kucherenko | Low | Fixed | Fixed | 24/Sep/15 6:42 AM | 12/Oct/15 12:40 AM
VMI-2765 | API: Post JSON response object throws JsonSyntaxException | Ryan Taylor | Highest | Fixed | Fixed | 23/Sep/15 2:58 PM | 27/Oct/15 10:58 AM
VMI-2763 | Android: Close button in Action Menu | Toma Panina | Low | Fixed | Fixed | 23/Sep/15 7:00 AM | 07/Oct/15 12:35 AM
VMI-2762 | Android: Duplicating of song on Artists page | Toma Panina | Low | Working As Designed | Won't Fix | 23/Sep/15 6:48 AM | 06/Oct/15 1:43 AM
VMI-2756 | iOS: Wrong screen return from the window "Artist User" | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 23/Sep/15 2:56 AM | 30/Oct/15 7:30 AM
VMI-2755 | IOS: When clicked Add to Favorites button text does not changes to "Remove from Favorite" | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 23/Sep/15 2:44 AM | 08/Oct/15 3:20 AM
VMI-2754 | IOS: No menu appears when you press the 'Share' button | Alexey Dudarev [QA] | Normal | Working As Designed | Won't Fix | 23/Sep/15 1:53 AM | 17/Nov/15 11:27 PM
VMI-2753 | IOS: 'Share' button doesn't work for the IOS platform | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 23/Sep/15 12:49 AM | 17/Nov/15 11:28 PM
VMI-2750 | iOS: Left swipe should be disabled while in SongBrowseController | Thuy Copeland | Normal | Ready For Testing | Unresolved | 22/Sep/15 8:49 PM | 17/Nov/15 10:19 AM
VMI-2741 | Android: Search does not return results and does not display why | Barton Stanley | Low | Fixed | Fixed | 22/Sep/15 1:17 PM | 06/Oct/15 10:21 AM
VMI-2731 | IOS: The small translucent popup does not appears when Remove from favorites | Alexey Dudarev [QA] | Normal | Working As Designed | Won't Fix | 22/Sep/15 7:54 AM | 28/Sep/15 11:15 PM
VMI-2730 | IOS: The small translucent popup does not appears when Add to Favorites | Alexey Dudarev [QA] | Normal | Working As Designed | Won't Fix | 22/Sep/15 7:50 AM | 28/Sep/15 11:15 PM
VMI-2729 | Android: Songs of the selected artist does not appears in the playlist after add to playlist their. | Alexey Dudarev [QA] | Normal | Working As Designed | Won't Fix | 22/Sep/15 6:57 AM | 28/Sep/15 11:15 PM
VMI-2728 | Android: Wrong screen return from the window "Share" | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 6:25 AM | 01/Oct/15 5:20 AM
VMI-2727 | Android: The small translucent popup contains incorrect message with text "Your post has been shared" | Alexey Dudarev [QA] | Normal | Working As Designed | Won't Fix | 22/Sep/15 6:20 AM | 17/Nov/15 4:44 PM
VMI-2726 | Android: The small translucent popup does not appears when Add to Favorites | Alexey Dudarev [QA] | Normal | Ready For Testing | Incomplete | 22/Sep/15 5:29 AM | 01/Oct/15 5:20 AM
VMI-2725 | Android: Update action menu: Song | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 5:22 AM | 29/Sep/15 7:29 AM
VMI-2724 | iOS: The small translucent popup does not appears when Add to queue | Alexey Dudarev [QA] | Normal | Working As Designed | Won't Fix | 22/Sep/15 4:41 AM | 28/Sep/15 11:15 PM
VMI-2723 | IOS: When add song to playlist, the app crashes | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 4:34 AM | 06/Oct/15 7:22 AM
VMI-2722 | IOS: The small translucent popup does not appears when Add to Playlist | Alexey Dudarev [QA] | Normal | Working As Designed | Won't Fix | 22/Sep/15 4:31 AM | 28/Sep/15 11:15 PM
VMI-2721 | Android: No "Go-Live" button in FSP - (Pos 1) (Share Live = N) if tap a song from playlist | Olga Tsygankova | None | Fixed | Fixed | 22/Sep/15 3:44 AM | 07/Oct/15 1:32 PM
VMI-2720 | iOS: Folder Action Menu doesn't work | Toma Panina | Low | Working As Designed | Won't Fix | 22/Sep/15 3:35 AM | 22/Sep/15 9:04 AM
VMI-2719 | Android: The small translucent popup does not appears when Add to queue | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 3:22 AM | 02/Oct/15 9:24 AM
VMI-2718 | IOS: Add to Queue doesn't work for the IOS platform | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 3:02 AM | 08/Oct/15 3:17 AM
VMI-2716 | IOS: Add to Playlist button doesn't work for the IOS platform | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 2:54 AM | 11/Oct/15 1:41 PM
VMI-2715 | Android: The artist isn't placed in the playlist. | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 2:54 AM | 06/Oct/15 3:59 AM
VMI-2714 | The contents and order of the "Artist Action Menu" are different for IOS and Android platforms. | Alexey Dudarev [QA] | Normal | Fixed | Fixed | 22/Sep/15 2:26 AM | 01/Oct/15 5:37 AM
VMI-2713 | iOS: Filter bar in folder is always displayed on the screen | Toma Panina | Low | Fixed | Fixed | 22/Sep/15 1:30 AM | 07/Oct/15 12:29 AM
VMI-2712 | iOS: Incorrect order in folder list | Toma Panina | Normal | Working As Designed | Won't Fix | 22/Sep/15 1:19 AM | 22/Sep/15 1:26 PM
VMI-2711 | Android: Incorrect Play Controls in FSP - (Pos 1) (Share Live = N) | Olga Tsygankova | None | Fixed | Fixed | 22/Sep/15 1:07 AM | 07/Oct/15 1:32 PM
VMI-2709 | Android: Incorrect video commenting screen in FSP (Pos 2) - Video commenting (Share Live = Y) if seconf time press and hold V/P Button | Olga Tsygankova | None | Fixed | Fixed | 22/Sep/15 12:03 AM | 07/Oct/15 1:32 PM
VMI-2708 | iOS: No Progress Bar in FSP - Video commenting (Pos 2) (Share Live = Y) | Olga Tsygankova | None | Fixed | Fixed | 21/Sep/15 11:25 PM | 05/Oct/15 4:07 AM
VMI-2706 | iOS: After tapping "done" button from song browser screen, app crashes | Thuy Copeland | Normal | Fixed | Fixed | 21/Sep/15 5:16 PM | 06/Oct/15 7:25 AM
VMI-2705 | iOS: Adding songs to playlist does not show "done" and "cancel" buttons | Thuy Copeland | Normal | Ready For Testing | Unresolved | 21/Sep/15 5:13 PM | 09/Oct/15 1:48 PM
VMI-2698 | iOS: Adding a song to playlist causes crash | Thuy Copeland | Normal | Working As Designed | Won't Fix | 21/Sep/15 11:14 AM | 01/Oct/15 4:29 PM
VMI-2697 | OSX client stops uploading, and adding media files to playlists | Alex Savenok | Highest | Ready For Testing | Unresolved | 21/Sep/15 10:07 AM | 08/Oct/15 11:21 PM
VMI-2693 | Android: Incorrect audio commenting screen. (no Timer) | Olga Tsygankova | Normal | Fixed | Fixed | 21/Sep/15 6:47 AM | 07/Oct/15 1:32 PM
VMI-2692 | iOS: Incorrect Track Timestamp - Passed and Track Timestamp - Remaining in FSP (Pos 2,3) (Share Live = Y) | Olga Tsygankova | None | Fixed | Fixed | 21/Sep/15 6:22 AM | 08/Nov/15 10:43 PM
VMI-2691 | iOS: No the track name in FSP (Pos 2,3) - Video commening, Audio commening (Share Live = Y) | Olga Tsygankova | None | Fixed | Fixed | 21/Sep/15 6:05 AM | 05/Oct/15 4:08 AM
VMI-2690 | iOS: The application freezes after tapping album in "My Collection - Albums" tab | Aleksey Sofronov | Low | Fixed | Fixed | 21/Sep/15 6:01 AM | 06/Oct/15 4:28 AM
VMI-2688 | Desktop: Change of track info isn't synced with library | Aleksey Sofronov | Normal | Working As Designed | Won't Fix | 21/Sep/15 4:00 AM | 22/Sep/15 11:47 PM
VMI-2687 | iOS: Incorrect the background image in FSP (Pos 3) - Audio comments (Share Live = Y) | Olga Tsygankova | None | Fixed | Fixed | 21/Sep/15 4:00 AM | 27/Oct/15 7:09 AM
VMI-2686 | Android: Incorrect the background image in FSP (Pos 3) - Audio comments (Share Live = Y) | Olga Tsygankova | None | Fixed | Fixed | 21/Sep/15 3:56 AM | 07/Oct/15 1:32 PM
VMI-2685 | Desktop: Structure of media library changes in iTunes during the first sync | Aleksey Sofronov | High | Fixed | Fixed | 21/Sep/15 1:24 AM | 23/Sep/15 4:17 AM
VMI-2675 | iOS: Following broadcast isn't visible in "ListenIn - Following" tab | Aleksey Sofronov | High | Working As Designed | Won't Fix | 18/Sep/15 7:41 AM | 22/Sep/15 10:04 AM
VMI-2674 | Android: Broadcast can't be played back from "ListenIn - Followings" tab | Aleksey Sofronov | High | Ready For Testing | Unresolved | 18/Sep/15 7:36 AM | 16/Nov/15 4:53 AM
VMI-2673 | Services: Deletion of folders from iTunes isn't synced with user's library | Aleksey Sofronov | High | Working As Designed | Won't Fix | 18/Sep/15 6:34 AM | 20/Oct/15 6:51 AM
VMI-2672 | Services: Video commentary stream can not be played by iOS / Mac OS X | Sergey Bobrovsky | Low | Ready For Testing | Unresolved | 18/Sep/15 5:07 AM | 12/Nov/15 10:08 AM
VMI-2671 | Services: Broadcast video created from static image is rotated 90 degrees CCW | Sergey Bobrovsky | Stop everything! | Fixed | Fixed | 18/Sep/15 3:51 AM | 07/Oct/15 11:32 PM
VMI-2652 | Load Environment: There is no possible to register users on loadstack | Viktor Dudnik | Stop everything! | Fixed | Fixed | 18/Sep/15 12:42 AM | 12/Oct/15 2:00 PM
VMI-2651 | API: Post token unit test fixes | Sai Chow | Normal | Fixed | Fixed | 18/Sep/15 12:31 AM | 26/Sep/15 7:50 AM
VMI-2650 | API: /listenin/trending response structure need to be the same as /listenin/following | Sai Chow | Highest | Fixed | Fixed | 18/Sep/15 12:26 AM | 27/Oct/15 12:25 AM
VMI-2635 | Fix Date serialization issue | Constantine Yannuck | Highest | Fixed | Fixed | 17/Sep/15 12:32 PM | 22/Sep/15 4:12 AM
VMI-2610 | Make Uploader for different environments | Vitaly Urazov | High | Fixed | Fixed | 16/Sep/15 7:46 AM | 23/Sep/15 6:47 AM
VMI-2598 | Desktop: An error during uninstallation | Aleksey Sofronov | Low | Fixed | Fixed | 16/Sep/15 12:55 AM | 21/Sep/15 12:34 AM
VMI-2595 | iOS: When Share Live the first time, the end of the count down pause for a while until FSP shows up | Sai Chow | High | Fixed | Fixed | 15/Sep/15 10:34 PM | 30/Sep/15 9:14 AM
VMI-2594 | Services: The video layer does not contain the background image when no video comment is in place | Sai Chow | Highest | Ready For Testing | Unresolved | 15/Sep/15 10:30 PM | 17/Sep/15 2:45 AM
VMI-2593 | iOS: The video layer is incorrect | Sai Chow | High | Fixed | Fixed | 15/Sep/15 10:26 PM | 13/Nov/15 1:35 AM
VMI-2565 | Folder or playlist isn't moved to folder after sync with desktop | Vitaly Urazov | High | Fixed | Fixed | 15/Sep/15 4:29 AM | 17/Sep/15 3:17 AM
VMI-2558 | API: Incorrect search results on Integration | Ryan Taylor | Stop everything! | Fixed | Fixed | 14/Sep/15 6:50 PM | 22/Oct/15 3:18 AM
VMI-2553 | Android: Missing user info | Kelly Schrock | High | Fixed | Fixed | 14/Sep/15 4:14 PM | 05/Oct/15 9:44 PM
VMI-2550 | PUT /sync/changes/ services error on QA | Thuy Copeland | Stop everything! | Working As Designed | Won't Fix | 14/Sep/15 10:30 AM | 14/Sep/15 10:44 AM
VMI-2545 | Service: Errors prevent apps from being able to listen to broadcast | Sergey Bobrovsky | Stop everything! | Fixed | Fixed | 14/Sep/15 3:05 AM | 18/Sep/15 7:41 AM
VMI-2542 | iOS: App crashes with EXC_BAD_ACCESS when left running for hours | Sergey Bobrovsky | Normal | In Progress | Incomplete | 14/Sep/15 12:55 AM | 17/Nov/15 5:04 PM
VMI-2531 | Android: All elements in all action menus in version 1.3.5 have the same IDs | Alexander Malyshkin | High | Fixed | Fixed | 11/Sep/15 5:20 AM | 06/Oct/15 5:53 AM
VMI-2528 | Services:AlbumID and ArtistID are not stored on server | Iliya Sivkov | Normal | Working As Designed | Won't Fix | 11/Sep/15 4:47 AM | 23/Sep/15 3:25 AM
VMI-2517 | Android: Camera issues on Samsung devices | Kelly Schrock | High | Fixed | Fixed | 10/Sep/15 8:55 AM | 17/Sep/15 8:28 AM
VMI-2514 | "bad" is not a number | Kelly Schrock | High | Fixed | Fixed | 09/Sep/15 5:23 PM | 22/Sep/15 10:18 AM
VMI-2513 | User token authentication incompletely implemented | Kelly Schrock | Highest | Fixed | Fixed | 09/Sep/15 3:12 PM | 06/Oct/15 11:55 AM
VMI-2505 | java.io.FileNotFoundException for URL to uploaded file Amazon S3 | Vitaly Urazov | Stop everything! | Fixed | Fixed | 09/Sep/15 6:42 AM | 12/Oct/15 2:00 PM
VMI-2503 | Mac Desktop: Correct warning message doesn't exist when iTunes isn't installed | Aleksey Sofronov | Low | Fixed | Fixed | 09/Sep/15 5:02 AM | 11/Sep/15 7:38 AM
VMI-2498 | Desktop: If user doesn't have library, desktop application crashes after login | Aleksey Sofronov | Normal | Fixed | Fixed | 09/Sep/15 3:41 AM | 22/Sep/15 8:33 AM
VMI-2497 | iOS: User's library isn't created after user's registration and login to mobile application | Aleksey Sofronov | Normal | Working As Designed | Won't Fix | 09/Sep/15 3:35 AM | 22/Sep/15 10:01 AM
VMI-2490 | Android: Next Track not playing | Kelly Schrock | Highest | Fixed | Fixed | 08/Sep/15 3:38 PM | 30/Oct/15 7:31 AM
VMI-2489 | API: Cover art not displayed in My Collection - Songs | Kelly Schrock | High | Fixed | Fixed | 08/Sep/15 3:07 PM | 06/Oct/15 7:12 AM
VMI-2471 | Android: No folder name is displayed on a folder landing page | Alexander Malyshkin | Low | Fixed | Fixed | 08/Sep/15 7:11 AM | 24/Sep/15 7:32 AM
VMI-2470 | iOS: `Settings` page is completely blank | Alexander Malyshkin | Normal | Working As Designed | Won't Fix | 08/Sep/15 6:33 AM | 09/Sep/15 1:49 AM
VMI-2469 | iOS: Incorrect audio commenting screen | Olga Tsygankova | Normal | Working As Designed | Won't Fix | 08/Sep/15 6:28 AM | 22/Sep/15 10:15 AM
VMI-2467 | Android: There are neither `Share` nor `Back` buttons in `Post to My Feed` dialog | Alexander Malyshkin | Normal | Fixed | Fixed | 08/Sep/15 6:12 AM | 10/Sep/15 4:14 AM
VMI-2464 | iOS: Video mode is initiated without the flash (flash=ON) (FSP - Pos 2) | Olga Tsygankova | Normal | Fixed | Fixed | 08/Sep/15 5:56 AM | 05/Oct/15 4:06 AM
VMI-2463 | Android: Video mode is initiated without the flash (flash=ON) (FSP - Pos 2) | Olga Tsygankova | Normal | Fixed | Fixed | 08/Sep/15 5:55 AM | 05/Oct/15 4:13 AM
VMI-2462 | iOS: Sync fetches no data after automatic migration to a new Core Data schema | Sergey Bobrovsky | Stop everything! | Fixed | Fixed | 08/Sep/15 5:53 AM | 22/Sep/15 7:48 AM
VMI-2461 | Desktop: Deleted track isn't synced with desktop application | Aleksey Sofronov | Normal | Fixed | Fixed | 08/Sep/15 5:42 AM | 17/Sep/15 7:48 AM
VMI-2460 | Android: Application is failed when the song finished playing in FSP | Olga Tsygankova | Normal | Fixed | Fixed | 08/Sep/15 5:30 AM | 30/Sep/15 8:44 AM
VMI-2458 | iOS: Neither folder nor playlist can be created | Alexander Malyshkin | Normal | Fixed | Fixed | 08/Sep/15 3:34 AM | 07/Oct/15 12:32 AM
VMI-2457 | Android: Incorrect Radio Station Item Type | Olga Tsygankova | None | New | Unresolved | 08/Sep/15 2:32 AM | 02/Nov/15 1:18 AM
VMI-2456 | iOS: Incorrect list of recommended stations from Pandora | Olga Tsygankova | None | Working As Designed | Won't Fix | 08/Sep/15 2:08 AM | 02/Nov/15 1:19 AM
VMI-2453 | API: Execution /uploader/file/{fileUuid} with Access Token another user | Olga Tsygankova | None | Working As Designed | Won't Fix | 07/Sep/15 8:50 AM | 12/Oct/15 5:33 PM
VMI-2452 | API: Execution /uploader/GetFileUrl/{fileUuid} with Access Token another user | Olga Tsygankova | None | Working As Designed | Won't Fix | 07/Sep/15 8:46 AM | 12/Oct/15 5:32 PM
VMI-2451 | API: Execution uploader/upload/{uploadUuid}/complete with Access Token another user | Olga Tsygankova | None | Working As Designed | Won't Fix | 07/Sep/15 8:41 AM | 12/Oct/15 5:26 PM
VMI-2447 | Android: Editing of playlist doesn't work correctly in "My Collection" | Aleksey Sofronov | Normal | Fixed | Fixed | 07/Sep/15 3:19 AM | 30/Oct/15 7:29 AM
VMI-2443 | Desktop: If track from iCloud is played back, its non-named copy is created | Aleksey Sofronov | Normal | Valid | Unresolved | 07/Sep/15 12:50 AM | 04/Nov/15 5:26 AM
VMI-2442 | iOS: Synchronization doesn't work for Vertigo mobile client | Aleksey Sofronov | Stop everything! | Blocked | Incomplete | 06/Sep/15 12:02 PM | 17/Nov/15 10:06 AM
VMI-2439 | Android: Media player performance | Kelly Schrock | High | New | Unresolved | 04/Sep/15 12:08 PM | 04/Sep/15 12:08 PM
VMI-2437 | Desktop: Icon changes to default java after user logs in | Aleksey Sofronov | Low | Blocked | Unresolved | 04/Sep/15 7:23 AM | 25/Oct/15 3:24 AM
VMI-2436 | Desktop: Change of Artwork (CoverArt) of album isn't synced with user library | Aleksey Sofronov | Normal | Fixed | Fixed | 04/Sep/15 7:13 AM | 22/Sep/15 8:32 AM
VMI-2435 | Android: Message "Broadcast session failed" appears | Olga Tsygankova | None | Working As Designed | Won't Fix | 04/Sep/15 6:39 AM | 09/Sep/15 1:47 AM
VMI-2434 | Android: "Repeat" button works incorrect | Olga Tsygankova | Normal | In Progress | Unresolved | 04/Sep/15 6:24 AM | 16/Nov/15 5:05 AM
VMI-2433 | Android: Changes aren't synced until user relogs | Aleksey Sofronov | Normal | Fixed | Fixed | 04/Sep/15 6:16 AM | 17/Sep/15 7:53 AM
VMI-2432 | Android: "Previous" button works incorrect | Olga Tsygankova | Normal | Fixed | Fixed | 04/Sep/15 6:15 AM | 05/Oct/15 2:20 AM
VMI-2431 | Android: No "Like" button in FSP - (Share Live = N) - Pos. 1 - Implement Regular Player | Olga Tsygankova | Normal | Fixed | Fixed | 04/Sep/15 6:10 AM | 30/Oct/15 6:10 AM
VMI-2430 | Android: Album isn't synced for uploaded song | Aleksey Sofronov | Normal | Fixed | Fixed | 04/Sep/15 6:08 AM | 02/Oct/15 7:44 AM
VMI-2429 | Android: Incorrect Song Details in FSP - (Share Live = N) - Pos. 1 - Implement Regular Player | Olga Tsygankova | Normal | Fixed | Fixed | 04/Sep/15 5:44 AM | 30/Oct/15 1:04 AM
VMI-2428 | Android: Application is failed after pressing "Queue" button in the FSP | Olga Tsygankova | None | Fixed | Fixed | 04/Sep/15 5:32 AM | 17/Sep/15 8:39 AM
VMI-2427 | Desktop: App cannot be started after it was installed for the first time | Alexander Malyshkin | Low | In Progress | Unresolved | 04/Sep/15 4:03 AM | 22/Sep/15 8:45 AM
VMI-2425 | Sync service continue to send the same data after previous syncs | Sai Chow | Normal | Fixed | Fixed | 04/Sep/15 1:03 AM | 22/Sep/15 7:30 AM
VMI-2424 | API: Search parameter might be incorrect | Sai Chow | High | Fixed | Fixed | 03/Sep/15 9:22 PM | 29/Oct/15 10:07 AM
VMI-2397 | Android: Event position always 0 on broadcast | Kelly Schrock | Normal | Fixed | Fixed | 03/Sep/15 8:53 AM | 03/Sep/15 8:55 AM
VMI-2389 | iOS: Transition between FSP and mini player is not very smooth | Sai Chow | Normal | Fixed | Fixed | 03/Sep/15 12:58 AM | 12/Nov/15 6:00 AM
VMI-2388 | iOS: When listening to music in FSP, earbuds cause abnormal behavior | Sai Chow | Normal | Working As Designed | Won't Fix | 03/Sep/15 12:56 AM | 25/Sep/15 6:54 AM
VMI-2381 | Android: App crashes on "My Collection" from menu | Kelly Schrock | Highest | Fixed | Fixed | 02/Sep/15 4:42 PM | 06/Oct/15 9:16 AM
VMI-2380 | Android: Failed sign-up has meaningless error message | Kelly Schrock | Normal | New | Unresolved | 02/Sep/15 4:10 PM | 02/Sep/15 4:43 PM
VMI-2379 | Android: App refuses to close on "Back" from sign-in screen | Kelly Schrock | Normal | Fixed | Fixed | 02/Sep/15 2:46 PM | 01/Oct/15 11:45 PM
VMI-2376 | iOS: App crashes if LandingContainerViewController is in edit mode and starts animating sliding effect after dragging. | Peter Vibe | Normal | Fixed | Fixed | 02/Sep/15 11:09 AM | 24/Sep/15 7:26 AM
VMI-2373 | iOS: Back button is distorted if the title is too long on landing pages. | Peter Vibe | Normal | Fixed | Fixed | 02/Sep/15 8:25 AM | 24/Sep/15 7:25 AM
VMI-2363 | iOS: Camera feature missing in Profile (due to old Verticast screen removal) | Sai Chow | High | Fixed | Fixed | 02/Sep/15 12:10 AM | 22/Sep/15 10:12 AM
VMI-2352 | iOS: Example app doesn't play when tapping accessory view | Jay Whitsitt | Lowest | New | Unresolved | 01/Sep/15 12:18 PM | 01/Sep/15 12:19 PM
VMI-2305 | Android: Artist name, count of songs and their duration aren't displayed for album | Aleksey Sofronov | Low | Fixed | Fixed | 29/Aug/15 7:04 AM | 30/Aug/15 5:01 PM
VMI-2304 | Android: Tracks are displayed in alphabethical order in album on the album landing page | Aleksey Sofronov | Low | Fixed | Fixed | 29/Aug/15 6:54 AM | 02/Oct/15 8:00 AM
VMI-2303 | Android: Deletion of items aren't synced with the library | Aleksey Sofronov | Normal | Fixed | Fixed | 29/Aug/15 6:17 AM | 02/Oct/15 6:19 AM
VMI-2296 | User services should return 500 on sign up if it cannot add user to search | Alex Savenok | Highest | In Progress | Unresolved | 28/Aug/15 11:28 AM | 13/Oct/15 3:22 AM
VMI-2290 | Android: Broadcast session fails | Viktor Dudnik | None | Fixed | Fixed | 28/Aug/15 12:49 AM | 01/Sep/15 12:25 PM
VMI-2289 | iOS: Playback rate doesn't drop to 0 after 404 | Jay Whitsitt | Normal | Fixed | Fixed | 27/Aug/15 8:45 PM | 09/Sep/15 12:48 PM
VMI-2279 | Put user returned error, but user was created | Artem Golubnichenko | Low | Working As Designed | Won't Fix | 27/Aug/15 4:00 AM | 17/Nov/15 4:44 PM
VMI-2247 | Android: The value of "Track Timestamp - Remaining" is not decreasing when a song plays | Viktor Dudnik | None | Fixed | Fixed | 26/Aug/15 7:25 AM | 06/Oct/15 6:59 AM
VMI-2246 | Android: Filter menu is not pop-down on "Playlists" tab if list is empty | Viktor Dudnik | None | Fixed | Fixed | 26/Aug/15 6:06 AM | 06/Oct/15 6:48 AM
VMI-2245 | Android: Vertigo App crashes if add a song through "Playlist Action Menu" | Viktor Dudnik | None | Fixed | Fixed | 26/Aug/15 5:32 AM | 17/Sep/15 8:09 AM
VMI-2244 | Android: Song is not removed from playlist immediately after it was deleted through the "Song Action Menu" | Viktor Dudnik | Low | Fixed | Fixed | 26/Aug/15 5:16 AM | 22/Sep/15 11:38 PM
VMI-2243 | ElasticSearch: can not execute too many deleteBroadcast, deleteUser requests at the same time | Dmitry Konstantinov | High | Fixed | Fixed | 26/Aug/15 5:08 AM | 14/Oct/15 9:53 AM
VMI-2241 | Android: Song list overlaps playlist content | Viktor Dudnik | None | Fixed | Fixed | 26/Aug/15 4:53 AM | 22/Sep/15 11:28 PM
VMI-2240 | Android: A song is not played if tap on the song in a playlist | Viktor Dudnik | None | Fixed | Fixed | 26/Aug/15 4:13 AM | 22/Sep/15 11:39 PM
VMI-2207 | Android: A song is not played if tap on the song in "Favorites" | Olga Tsygankova | None | Ready For Testing | Unresolved | 25/Aug/15 8:03 AM | 06/Oct/15 6:58 AM
VMI-2206 | Android: A song is not downloaded | Olga Tsygankova | None | Working As Designed | Won't Fix | 25/Aug/15 7:50 AM | 27/Aug/15 12:14 AM
VMI-2205 | Android: A song is not added to the playlist | Olga Tsygankova | None | Fixed | Fixed | 25/Aug/15 7:44 AM | 17/Sep/15 8:10 AM
VMI-2204 | Android: incorrectly displays the number of albums and the number of songs on "Go to Artist" screen | Olga Tsygankova | None | Ready For Testing | Unresolved | 25/Aug/15 7:38 AM | 08/Oct/15 5:51 AM
VMI-2202 | iOS: When the song is deleted from "Songs" tab, it is not deleted from the playlist | Olga Tsygankova | Normal | Ready For Testing | Unresolved | 25/Aug/15 3:10 AM | 17/Nov/15 10:08 AM
VMI-2201 | iOS: Incorrect screen "Go to Album" | Olga Tsygankova | Normal | Fixed | Fixed | 25/Aug/15 2:42 AM | 24/Sep/15 7:29 AM
VMI-2200 | iOS: Incorrect screen "Go to Artist" | Olga Tsygankova | Normal | Fixed | Fixed | 25/Aug/15 2:40 AM | 24/Sep/15 7:29 AM
VMI-2199 | iOS: The icon "Go-Live" does not rotate 90 degrees clockwise when you tap and hold "Go-Live" button | Olga Tsygankova | Normal | Working As Designed | Won't Fix | 25/Aug/15 1:51 AM | 31/Aug/15 1:49 AM
VMI-2198 | iOS: "Unable to load followers" error appears when you tap on the Group Configuration icon | Olga Tsygankova | Normal | New | Unresolved | 25/Aug/15 1:16 AM | 02/Nov/15 1:09 AM
VMI-2176 | When opening Album/Artist/Playlist landing pages iOS app crashes. | Alex Savenok | High | Fixed | Fixed | 21/Aug/15 12:10 PM | 24/Sep/15 7:23 AM
VMI-2175 | OS X client stops syncing when importing remote playlist structure to empty iTunes | Alex Savenok | High | Fixed | Fixed | 21/Aug/15 11:55 AM | 03/Nov/15 5:08 AM
VMI-2159 | API layer damaging request strings (Broadcast) | Kelly Schrock | Highest | Fixed | Fixed | 20/Aug/15 4:34 PM | 21/Aug/15 9:18 AM
VMI-2158 | NetworkStateEventProducer crashing the app | Kelly Schrock | Highest | Fixed | Fixed | 20/Aug/15 2:18 PM | 11/Sep/15 1:08 PM
VMI-2152 | Desktop: First time login creates many folders and playlist | Sai Chow | Normal | Working As Designed | Won't Fix | 20/Aug/15 3:05 AM | 02/Nov/15 7:05 AM
VMI-2104 | The `/media` api isn’t decoding the `image_url` correctly. `%` symbols should decode as `%` and not as `%25` in links | Dmitriy Dorkin | Highest | Fixed | Fixed | 19/Aug/15 2:38 AM | 20/Aug/15 11:04 AM
VMI-2077 | Android: My Collections - Album does not show the right number of songs and not order correctly | Sai Chow | Normal | Ready For Testing | Incomplete | 18/Aug/15 12:02 AM | 04/Nov/15 11:41 PM
VMI-2076 | iOS: Action menu should not allow user to swipe to reveal main menu | Sai Chow | Normal | Working As Designed | Won't Fix | 17/Aug/15 11:28 PM | 17/Sep/15 11:36 AM
VMI-2068 | Application crashes when tapping the song in a queue | Nickolay Chernov | Normal | Fixed | Fixed | 17/Aug/15 12:22 AM | 22/Sep/15 5:01 AM
VMI-2052 | Application crashes after restart, if iTunes is opened before application starts | Alex Savenok | Low | Fixed | Fixed | 13/Aug/15 8:17 PM | 16/Sep/15 1:51 PM
VMI-2012 | iOS: crash at [MediaFile fileWithObjectID:inContext: MediaFile.m line 12 | Sai Chow | Normal | Working As Designed | Won't Fix | 13/Aug/15 1:59 AM | 17/Sep/15 11:37 AM
VMI-2010 | iOS: EventDispatcher crashes every once in a while | Sai Chow | Normal | Fixed | Fixed | 13/Aug/15 1:54 AM | 13/Nov/15 1:35 AM
VMI-2009 | iOS: Crashes in follower screen from profile when there are no followers | Sai Chow | Normal | Fixed | Fixed | 13/Aug/15 1:51 AM | 19/Aug/15 9:14 AM
VMI-2001 | CannotReadException: This file does not appear to be an Mp4 Audio file, could be corrupted or video | Vitaly Urazov | Highest | Fixed | Fixed | 12/Aug/15 4:17 AM | 09/Nov/15 10:36 AM
VMI-1945 | Android: The fields aren't named on sign up and login page | Aleksey Sofronov | Low | Fixed | Fixed | 10/Aug/15 12:53 AM | 17/Sep/15 8:13 AM
VMI-1940 | Entity Id's are not being assigned to uploaded tracks. | Alex Savenok | Low | Fixed | Fixed | 09/Aug/15 11:02 PM | 12/Oct/15 2:51 PM
VMI-1937 | Failed login shows "401 Unauthorized" message | Kelly Schrock | Normal | Fixed | Fixed | 07/Aug/15 3:40 PM | 09/Sep/15 1:28 AM
VMI-1921 | Library web client doesn't sort playlist items in playlist | Artem Golubnichenko | Low | Fixed | Fixed | 07/Aug/15 12:30 AM | 07/Aug/15 1:25 AM
VMI-1894 | Android: Library data isn't synchronized upon logout | Alexander Malyshkin | Low | Fixed | Fixed | 06/Aug/15 5:21 AM | 02/Oct/15 7:46 AM
VMI-1820 | FSP: AudioRecord PositionNotificationListener not being called | Kelly Schrock | High | Fixed | Fixed | 05/Aug/15 11:13 AM | 05/Aug/15 4:08 PM
VMI-1819 | Fix data on elasticsearch.vertigomediagroup.com | Irina Gorbunova | High | Fixed | Fixed | 05/Aug/15 9:12 AM | 06/Aug/15 9:25 AM
VMI-1809 | Android: Some elements in version 1.3.1 have no ID | Alexander Malyshkin | Low | Fixed | Fixed | 05/Aug/15 1:57 AM | 11/Sep/15 5:20 AM
VMI-1807 | App crashes out of memory exception | Alex Savenok | Low | Fixed | Fixed | 05/Aug/15 12:19 AM | 14/Sep/15 7:48 AM
VMI-1806 | Playlist keep reloading, iTunes UI blinks | Alex Savenok | Low | Fixed | Fixed | 05/Aug/15 12:07 AM | 03/Nov/15 5:59 AM
VMI-1805 | Moving tracks within a playlist does not sync. If I change the position of a track in a playlist the change is not detected or synced. | Alex Savenok | Low | Fixed | Fixed | 04/Aug/15 11:26 PM | 22/Sep/15 8:25 AM
VMI-1804 | When dragging iCloud tracks into a playlist, the tracks changes do not get synced | Alex Savenok | Low | Fixed | Fixed | 04/Aug/15 11:25 PM | 25/Aug/15 10:05 AM
VMI-1803 | When a folder is moved from one folder to another the changes do not sync | Alex Savenok | High | Fixed | Fixed | 04/Aug/15 11:23 PM | 03/Nov/15 5:59 AM
VMI-1802 | iOS: Settings button missing | Jay Whitsitt | Low | New | Unresolved | 04/Aug/15 9:34 PM | 26/Sep/15 2:32 AM
VMI-1801 | iOS: Queue table view has bad divider lines | Jay Whitsitt | Low | New | Unresolved | 04/Aug/15 4:02 PM | 26/Sep/15 2:32 AM
VMI-1800 | iOS: Scrolling on a Search > More screen scrolls the navigation bar | Jay Whitsitt | Low | New | Unresolved | 04/Aug/15 3:58 PM | 26/Sep/15 2:30 AM
VMI-1799 | iOS: Some table views have white background | Jay Whitsitt | Low | New | Unresolved | 04/Aug/15 3:56 PM | 26/Sep/15 2:31 AM
VMI-1798 | iOS: Shouldn't ask for microphone permission in broadcast flow | Jay Whitsitt | Low | Working As Designed | Won't Fix | 04/Aug/15 3:43 PM | 26/Sep/15 4:58 PM
VMI-1797 | iOS: Data model should be versioned | Jay Whitsitt | Low | Working As Designed | Won't Fix | 04/Aug/15 3:39 PM | 26/Sep/15 2:28 AM
VMI-1796 | iOS: App Transport Security policy | Jay Whitsitt | High | New | Unresolved | 04/Aug/15 3:19 PM | 17/Nov/15 3:00 PM
VMI-1795 | iOS: Views rendered as iPhone 4s | Jay Whitsitt | Low | Ready For Testing | Unresolved | 04/Aug/15 3:17 PM | 04/Nov/15 12:15 AM
VMI-1793 | Android: Up button appears instead of navigation drawer icon | Ryan Taylor | Low | Fixed | Fixed | 04/Aug/15 12:33 PM | 21/Aug/15 3:37 PM
VMI-1791 | Android: App crashes when selecting Artist or Album without cover image | Nickolay Chernov | Normal | Fixed | Fixed | 04/Aug/15 5:05 AM | 02/Oct/15 7:44 AM
VMI-1787 | Android: There is an eternal loading indicator in the empty root folder/in an empty subfolder | Alexander Malyshkin | Low | Fixed | Fixed | 04/Aug/15 1:46 AM | 18/Sep/15 4:59 AM
VMI-1781 | iOS: demo mode does is not set correctly on staging plist and accounts throws error | Sai Chow | Normal | Fixed | Fixed | 03/Aug/15 10:11 AM | 23/Aug/15 11:06 PM
VMI-1768 | Desktop App: If add existing track to any playlist it is removed from the playlist | Aleksey Sofronov | Low | Fixed | Fixed | 03/Aug/15 2:31 AM | 08/Sep/15 4:42 AM
VMI-1753 | Desktop App: Correct launching isn't possible while track is played back | Aleksey Sofronov | Low | New | Unresolved | 31/Jul/15 9:36 AM | 31/Jul/15 9:37 AM
VMI-1751 | Desktop App rolls back changes that was made in iTunes before the application start | Aleksey Sofronov | Normal | In Progress | Unresolved | 31/Jul/15 8:38 AM | 18/Nov/15 12:54 AM
VMI-1750 | Desktop App: Tracks are duplicated in the default playlist "Music" in iTunes | Aleksey Sofronov | Normal | Blocked | Unresolved | 31/Jul/15 8:19 AM | 23/Sep/15 6:48 AM
VMI-1720 | When shuffle playing the orange border needs to stay lit as long as the app is in shuffle play | Alex Savenok | Low | Fixed | Fixed | 29/Jul/15 11:49 PM | 07/Aug/15 3:58 AM
VMI-1719 | Cannot like artist or albums on android | Alex Savenok | High | Fixed | Fixed | 29/Jul/15 11:47 PM | 04/Sep/15 5:43 AM
VMI-1696 | Android: App takes unacceptably long time before showing UI | Kelly Schrock | High | Fixed | Fixed | 27/Jul/15 10:46 AM | 31/Jul/15 8:33 AM
VMI-1685 | Vertigo Desktop MacOS. Incorrect display login window when the application starts. | Roman Deryabin | Low | Blocked | Unresolved | 27/Jul/15 1:31 AM | 25/Aug/15 6:46 AM
VMI-1684 | iOS: Playlist action menu does not behave like the other action menus | Sai Chow | Normal | Fixed | Fixed | 27/Jul/15 12:24 AM | 24/Sep/15 7:30 AM
VMI-1683 | Research problem with installer for Mac OS X | Artem Golubnichenko | Low | New | Unresolved | 26/Jul/15 10:27 PM | 10/Aug/15 5:33 AM
VMI-1658 | Search Service fails to retrieve user information | Alexander Altergot | Normal | Fixed | Fixed | 23/Jul/15 4:47 AM | 26/Jul/15 5:11 PM
VMI-1656 | After logging in, the app crashes after a minute or so | Sai Chow | Normal | Fixed | Fixed | 23/Jul/15 12:09 AM | 24/Aug/15 12:47 AM
VMI-1655 | Moving playlist/folder from subfolders to root | Artem Golubnichenko | Normal | In Progress | Unresolved | 22/Jul/15 11:41 PM | 07/Aug/15 2:48 AM
VMI-1654 | iOS: 500 response when creating new user | Jay Whitsitt | Low | Fixed | Fixed | 22/Jul/15 5:58 PM | 11/Aug/15 12:10 PM
VMI-1566 | API: connect/feed is missing a lot of values | Sai Chow | Stop everything! | Fixed | Fixed | 20/Jul/15 5:22 PM | 01/Oct/15 5:37 AM
VMI-1560 | NullPointerException in XMLImportPlugin | Artem Golubnichenko | Normal | Fixed | Fixed | 20/Jul/15 8:08 AM | 21/Jul/15 2:11 AM
VMI-1553 | Android: Vertiflip causes an ANR when calling VertigoBroadcaster.reset() | Kelly Schrock | High | Fixed | Fixed | 17/Jul/15 3:20 PM | 24/Jul/15 9:35 AM
VMI-1549 | Desktop App: Internal error when tracks are deleted before synchronization | Aleksey Sofronov | Normal | Fixed | Fixed | 17/Jul/15 2:24 AM | 29/Jul/15 4:52 AM
VMI-1536 | Mac installer for desktop app results in delays in syncing. | Alex Savenok | High | Fixed | Fixed | 16/Jul/15 10:37 AM | 03/Aug/15 5:52 PM
VMI-1501 | Android: FSP - Share Live - take photo fails after 2 times video recording | Andrew Kucherenko | Low | Fixed | Fixed | 15/Jul/15 3:04 AM | 24/Aug/15 2:28 AM
VMI-1497 | Android: DB fault preventing playback of "previous" track | Kelly Schrock | Normal | Fixed | Fixed | 14/Jul/15 2:25 PM | 17/Jul/15 11:45 AM
VMI-1495 | Android: Sync rolls back the changes when editing a playlist | Aleksey Sofronov | Low | Fixed | Fixed | 14/Jul/15 3:58 AM | 02/Oct/15 7:04 AM
VMI-1483 | Android: Incorrect synchronization of parameter 'Artist' for songs | Aleksey Sofronov | Normal | Blocked | Unresolved | 13/Jul/15 6:25 AM | 23/Sep/15 11:16 PM
VMI-1481 | Android: Sharing description hides under the top frame during typing | Aleksey Sofronov | Low | Fixed | Fixed | 13/Jul/15 5:08 AM | 18/Jul/15 10:54 AM
VMI-1478 | Android: Pull-down filter freezes on the screen | Aleksey Sofronov | Low | Working As Designed | Won't Fix | 13/Jul/15 3:48 AM | 03/Nov/15 1:53 AM
VMI-1477 | Android: Incorrect creation/editing titles of folders and playlists | Aleksey Sofronov | Normal | Ready For Testing | Unresolved | 13/Jul/15 3:34 AM | 22/Oct/15 11:06 PM
VMI-1475 | Android: The application crashes if tracks order has been changed in playlist | Aleksey Sofronov | Low | Fixed | Fixed | 13/Jul/15 3:07 AM | 18/Jul/15 11:04 AM
VMI-1472 | iOS: Browse - Song Action View - selecting artist/album causes crash | Thuy Copeland | Normal | Fixed | Fixed | 10/Jul/15 5:02 PM | 30/Jul/15 9:36 AM
VMI-1468 | Android: Search results are not implemented correctly | Sai Chow | Normal | Fixed | Fixed | 09/Jul/15 5:01 PM | 01/Oct/15 9:30 AM
VMI-1467 | iOS: Add playlist and playlist folder both crashes the app and Filter bar need to be hidden on load | Sai Chow | High | Fixed | Fixed | 09/Jul/15 4:10 PM | 08/Sep/15 3:35 AM
VMI-1461 | iOS: Search result for Profile is blank and layout incorrectly | Sai Chow | Normal | Fixed | Fixed | 09/Jul/15 1:24 AM | 02/Sep/15 5:35 AM
VMI-1456 | iOS: Search crashes | Sai Chow | Normal | Fixed | Fixed | 08/Jul/15 4:11 PM | 15/Jul/15 2:12 PM
VMI-1455 | JSON prototype: Browse uuids/real entities no longer work | Thuy Copeland | Normal | Fixed | Fixed | 08/Jul/15 12:15 PM | 21/Jul/15 11:12 PM
VMI-1454 | iOS: Browse like songs not working | Thuy Copeland | Normal | Fixed | Fixed | 08/Jul/15 12:12 PM | 30/Jul/15 9:36 AM
VMI-1453 | iOS: Selecting Artist/Album/Song in Browse causes app to crash | Thuy Copeland | Normal | Fixed | Fixed | 08/Jul/15 9:21 AM | 27/Jul/15 9:23 PM
VMI-1452 | Unable to login to UserService with Facebook or Twitter account | Nick Linker | Normal | Ready For Testing | Unresolved | 08/Jul/15 8:50 AM | 12/Nov/15 3:40 AM
VMI-1442 | Android: Fix Artist portrait drawable | Ryan Taylor | Normal | Fixed | Fixed | 07/Jul/15 4:36 PM | 05/Aug/15 12:18 AM
VMI-1441 | iOS: Add Test target back into the scheme and fix the compilation issue | Sai Chow | High | Fixed | Fixed | 07/Jul/15 2:16 PM | 27/Jul/15 9:23 PM
VMI-1440 | iOS: Unable to view Browse items in screens | Thuy Copeland | Normal | Fixed | Fixed | 07/Jul/15 12:12 PM | 16/Jul/15 8:24 AM
VMI-1438 | Incorrect processing of like requests if 'Like' button is tapped very fast | Aleksey Sofronov | Normal | Working As Designed | Won't Fix | 07/Jul/15 8:31 AM | 19/Oct/15 9:19 AM
VMI-1434 | Android: the application folds after relogin | Aleksey Sofronov | Low | Working As Designed | Won't Fix | 07/Jul/15 5:23 AM | 15/Jul/15 10:22 AM
VMI-1432 | After reordering items in playlist, some of them is duplicated | Vitaly Urazov | High | Fixed | Fixed | 07/Jul/15 1:38 AM | 23/Jul/15 3:11 AM
VMI-1431 | iOS: Reels crash when played | Sai Chow | Highest | Fixed | Fixed | 06/Jul/15 10:55 PM | 15/Jul/15 2:12 PM
VMI-1430 | iOS: Tap Go Live button from full screen player does not take you to Broadcast settings | Sai Chow | Highest | Working As Designed | Won't Fix | 06/Jul/15 9:53 PM | 27/Jul/15 9:23 PM
VMI-1428 | iOS: Unable to play music from Songs | Sai Chow | Highest | Fixed | Fixed | 06/Jul/15 4:44 PM | 15/Jul/15 2:12 PM
VMI-1427 | iOS: When Go Live from full screen player, it does not navigate to the Settings screen | Sai Chow | Highest | Fixed | Fixed | 06/Jul/15 3:20 PM | 27/Jul/15 9:23 PM
VMI-1425 | Android: Fix name collision with support library | Ryan Taylor | Normal | Fixed | Fixed | 06/Jul/15 2:27 PM | 15/Jul/15 10:22 AM
VMI-1417 | Android: Fix the tab "readjustment" motion | Ryan Taylor | Normal | Fixed | Fixed | 04/Jul/15 10:19 AM | 07/Aug/15 1:06 AM
VMI-1416 | Android: Fix navigation drawer slide gesture | Ryan Taylor | Normal | Fixed | Fixed | 04/Jul/15 10:12 AM | 07/Aug/15 2:37 AM
VMI-1378 | Android: Impossible to open FSP after closing it | Andrew Kucherenko | Normal | Fixed | Fixed | 03/Jul/15 3:36 AM | 12/Aug/15 7:52 AM
VMI-1377 | Android: Broadcast does not finish when "end" button is pressed | Andrew Kucherenko | Normal | Fixed | Fixed | 03/Jul/15 3:34 AM | 20/Aug/15 10:39 AM
VMI-1373 | Incorrect aspect ratio on video preview screen | Andrew Kucherenko | Normal | Fixed | Fixed | 03/Jul/15 1:54 AM | 27/Aug/15 11:30 PM
VMI-1367 | Android: User Profile swipe behavior | Kelly Schrock | High | Fixed | Fixed | 02/Jul/15 5:09 PM | 14/Aug/15 12:40 AM
VMI-1366 | Android: User Profile screen appearance | Kelly Schrock | High | Fixed | Fixed | 02/Jul/15 5:02 PM | 13/Aug/15 8:10 AM
VMI-1365 | Android: My Collection - Next song doesn't play automatically when a song completes | Kelly Schrock | Normal | Fixed | Fixed | 02/Jul/15 4:57 PM | 17/Jul/15 11:45 AM
VMI-1364 | Android: Enable tab switcher to save state | Kelly Schrock | Normal | Fixed | Fixed | 02/Jul/15 4:55 PM | 15/Jul/15 2:19 PM
VMI-1359 | Artist and profile borders are pixellated | Thuy Copeland | Normal | Fixed | Fixed | 02/Jul/15 1:19 PM | 15/Jul/15 2:19 PM
VMI-1358 | iOS: Browse - Featured - Tags cell should not scroll | Thuy Copeland | Normal | Fixed | Fixed | 02/Jul/15 1:13 PM | 27/Jul/15 9:24 PM
VMI-1283 | API: Error from search service as result of the request of editing profile to user service | Aleksey Sofronov | Low | Fixed | Fixed | 29/Jun/15 1:22 AM | 08/Jul/15 7:02 AM
VMI-1278 | When editing playlist moving tracks or deleting is very buggy | Alex Savenok | High | Fixed | Fixed | 28/Jun/15 11:14 PM | 30/Jul/15 10:26 AM
VMI-1274 | For greg@vertigomusic.com songs have duplicates, if I delete one of the duplicates, both get deleted. | Alex Savenok | Low | Working As Designed | Won't Fix | 28/Jun/15 10:21 PM | 28/Aug/15 2:43 AM
VMI-1273 | When adding track to playlist the track must be added to the end of the playlist | Alex Savenok | High | Fixed | Fixed | 28/Jun/15 9:53 PM | 18/Aug/15 12:55 AM
VMI-1267 | Search service returns null values. | Dmitriy Dorkin | Normal | Fixed | Fixed | 26/Jun/15 6:31 AM | 27/Oct/15 12:52 PM